## Slide 1
Causal Surgical World-Model Transfer
A Two-Paper Research Plan: Causal Benchmark + Privileged-Information Distillation
Follow-up to the BariatricRSD variability-scaling paper (NeurIPS 2026, E&D track).
Author: Bill
Status: 2026-05-21 · Plan + brief: NEXT_PAPER_PLAN.md, NEXT_PAPER_BRIEF.md

## Slide 2
Where we are
What the current paper (under review at NeurIPS 2026) established.
VARIABILITY-SCALING RESULT ON MB140 vs CHOLEC80
Findings
■ Workflow conditioning helps on MultiBypass140 (multi-center RYGB, K=6, H(z)=2.48).
■ Δ decoupled-oracle = −0.85 min within-center, −0.47 cross-center.
■ Statistically null on Cholec80 (single-center, K=4, H(z)=1.27, 71% of videos in one cluster).
■ Shuffled-token control rules out parameter-capacity explanation.
■ Pixel-only causal evaluator preserves −0.18 / −0.22 min without GT phases at test.
Methodology contributions
■ Strict prefix-only protocol — clip ends at prediction time t; removes future-frame leakage.
■ Decoupled-oracle architecture — phase head independent of workflow token; closes circularity.
■ Workflow-cluster apparatus — phase-bigram TF-IDF + PCA + k-means; offline + per-clip lookup.
■ Variability-scaling thesis — workflow conditioning's value tracks H(z) of phase-order clusters.
■ Causal-at-inference evaluator — soft cluster posterior from model's own prefix phase predictions.
BariatricRSD next-paper proposal · Slide 2 / 18
2026-05-21

## Slide 3
What's missing after the current paper
Gaps that justify the next-paper program.
RESEARCH GAPS
■ Training-time supervision gap. The pixel-only causal evaluator removes the inference-time oracle, but training still uses privileged phase + workflow labels.
■ No motion / action prediction. RSD is a scalar target. The model never says ‘what comes next’ — instrument changes, phase transitions, deviation events.
■ No engagement with the surgical-FM wave. SurgMotion, SurgVISTA, ZEN, EndoMamba, EndoDINO have appeared. Our framework hasn't been benchmarked against them.
■ Untested across procedures. MB140 + Cholec80 only. No cross-procedure transfer claims yet.
■ Untested under physical-AI world models. NVIDIA Cosmos and V-JEPA 2/2.1 transfer to surgical video is an open empirical question.
■ Variability-scaling thesis only on scalar RSD. Whether the H(z) pattern generalizes to anticipation tasks is the natural next probe.
BariatricRSD next-paper proposal · Slide 3 / 18
2026-05-21

## Slide 4
The research question
Survives any empirical outcome and isn't vendor-dependent.
ONE QUESTION THAT FRAMES BOTH PAPERS
Do physical-AI and surgical video foundation models improve causal surgical anticipation,
and does workflow variability still determine when explicit workflow-state conditioning helps?
Why this framing works:
■ Not vendor-locked — publishable whether Cosmos wins, loses, or ties.
■ Uses our strict prefix-only causal apparatus as the defining contribution.
■ Forces extension from scalar RSD to future-state prediction.
■ Tests whether the variability-scaling thesis generalizes.
BariatricRSD next-paper proposal · Slide 4 / 18
2026-05-21

## Slide 5
Two-paper plan
Split lets each contribution have depth and lets risk be hedged.
PAPERS 2A AND 2B SHARE ~70% INFRASTRUCTURE
PAPER 2A
Causal benchmark + foundation-model transfer matrix
Thesis: strict prefix-only evaluation re-ranks foundation models for surgical forecasting. Pixel-prediction quality is a weak proxy for downstream utility. Variability-scaling generalizes across backbones and tasks.
■ Target: MICCAI 2027 (Mar)
■ Compute: 1.5K–3.2K GPU-h
■ Risk: medium
■ Backup framing: ‘Cosmos-meh’ diagnostic
PAPER 2B
Privileged-information distillation for workflow-conditioned RSD
Thesis: a student model that learns the workflow posterior q(z | x_{≤t}) from a privileged teacher closes most of the oracle-to-deployable gap without using ground-truth phase or workflow labels at test.
■ Target: NeurIPS 2027 (May)
■ Compute: 0.75K–1.5K GPU-h
■ Risk: low (testable with existing assets)
■ Ships independent of FM transfer outcome
BariatricRSD next-paper proposal · Slide 5 / 18
2026-05-21

## Slide 6
Paper 2A — Innovation
Four claims that no competing surgical-FM paper has demonstrated.
WHY THIS PAPER ISN'T SCOOPABLE BY SURGMOTION / SURGVISTA / ZEN
■ 1. First causal evaluation protocol for surgical-video foundation models. Existing FM papers (SurgMotion, SurgVISTA, ZEN) report centered-window or aggregate metrics — none under strict prefix-only protocols matching deployment.
■ 2. First systematic transfer matrix that includes physical-AI world models alongside surgical-native FMs. No prior paper has tested Cosmos / V-JEPA 2.1 head-to-head against domain-specialized surgical FMs on the same downstream tasks.
■ 3. First diagnostic showing pixel-prediction quality is a weak proxy for downstream surgical forecasting. A measurement contribution to the broader world-model field, not just surgical AI.
■ 4. First multi-task variability-scaling extension. Current paper proved H(z) pattern on scalar RSD; Paper 2A extends to phase-transition anticipation and future-phase-sequence — demonstrating the pattern is task-general.
BariatricRSD next-paper proposal · Slide 6 / 18
2026-05-21

## Slide 7
Paper 2A — Experimental design
Frozen-feature transfer matrix × three causal anticipation tasks.
MODEL × TASK MATRIX
Backbone
RSD MAE
Next-transition MAE
Future-phase F1
Triplet mAP
Compute
ViT-B/16 (anchor)
✓
✓
✓
—
low
VideoMAE-L
✓
✓
✓
—
med
V-JEPA 2 / 2.1
✓
✓
✓
✓
med
Cosmos-Predict2
✓
✓
✓
—
high
SurgMotion
✓
✓
✓
✓
med
SurgVISTA / ZEN
✓
✓
✓
—
med
EndoMamba
✓
✓
—
—
low
Datasets & splits
■ MB140 within-center: 5-fold CV (fold 0 = dev fold)
■ MB140 cross-center: Bern → Strasbourg
■ Cholec80: 36/6/30 split
■ CholecT50: action-triplet anticipation (optional)
Conditions per (backbone, dataset)
■ no-token (baseline)
■ retrospective oracle (upper bound)
■ decoupled-oracle (closes circularity)
■ shuffled-token (semantic control)
BariatricRSD next-paper proposal · Slide 7 / 18
2026-05-21

## Slide 8
Paper 2A — Contribution to the field
What the surgical-AI / vision community gets after Paper 2A is published.
ARTIFACTS THE PAPER LEAVES BEHIND
Released artifacts
■ Causal anticipation benchmark — strict prefix-only RSD + phase + sequence evaluators.
■ Model-transfer leaderboard — anonymized per-backbone scores under matched protocol.
■ Pixel-quality-vs-downstream diagnostic — FVD/LPIPS/PSNR on a held-out surgical video set.
■ Reproducibility kit — code, configs, weights manifest, feature caches.
Field-level claims
■ Causal evaluation re-ranks FMs — leaderboards change under deployment-relevant protocols.
■ Surgical-native pretraining wins at matched compute — informs investment direction.
■ Pixel quality ≠ downstream utility — community must use task-relevant metrics.
■ Variability scaling is task-general — Cholec80 mis-calibration extends from RSD to anticipation.
BariatricRSD next-paper proposal · Slide 8 / 18
2026-05-21

## Slide 9
Paper 2B — Innovation
Closing the oracle-to-deployable gap with privileged-information distillation.
WHY DISTILLATION IS THE NEXT MOVE
CURRENT GAP
Train with privileged supervision → Test with pixels only
■ Oracle (privileged): −0.85 min
■ Deployable causal: −0.18 min
■ Gap to close: ~0.67 min
■ Lost mostly to noisy prefix-cluster posterior
METHOD
Teacher-student distillation for q_φ(z | x_{≤t})
■ Teacher: frozen decoupled-oracle model
■ Student: workflow posterior from pixels
■ Loss: RSD + phase + KL(posterior)
■ Eval: zero privileged signal at test
TARGET RESULT
Deployable predictor approaches privileged-supervision upper bound
■ Distilled student: ≤ 0.3 min from oracle
■ Variability scaling preserved
■ Cholec80 null preserved
■ Encoder-agnostic (ViT, V-JEPA, SurgMotion)
BariatricRSD next-paper proposal · Slide 9 / 18
2026-05-21

## Slide 10
Paper 2B — Method detail
Teacher-student distillation for the workflow posterior.
ARCHITECTURE
Surgical prefix
x_{≤t}
Visual encoder
(ViT / V-JEPA / SurgMotion)
Student q_φ(z | x_{≤t})
workflow posterior
Soft workflow token
Σ_k q_k · E_k
Temporal head
→ RSD / phase / next-transition
TRAINING ONLY — TEACHER SIGNAL
Full-video oracle cluster z(V) · prefix-derived cluster labels · phase-transition labels
→ KL distillation onto the student posterior q_φ; removed entirely at inference.
Loss
■ RSD regression (MSE)
■ Phase classification (CE, when labels available)
■ Next-transition regression / classification
■ Future-phase-sequence loss
■ KL distillation: q_φ ‖ teacher posterior
■ Optional calibration regularizer
Properties of the resulting student
■ Pixel-only at inference: no GT phases, no oracle cluster.
■ Calibrated: reliability diagram + ECE reported video-wise.
■ Variability-scaling preserved: Cholec80 remains null.
■ Encoder-agnostic: swap ViT for V-JEPA 2.1 or SurgMotion.
BariatricRSD next-paper proposal · Slide 10 / 18
2026-05-21

## Slide 11
Paper 2B — Contribution
What surgical AI gets from a working privileged-information distillation recipe.
DEPLOYABLE WORKFLOW CONDITIONING WITHOUT PRIVILEGED LABELS
Within-center MB140 strict val MAE (lower = better)
13.03 min
no-token (baseline)
12.85 min
deployable causal (current paper)
12.45 min
distilled student (target)
12.18 min
decoupled-oracle (privileged upper bound)
← target: close ≥ 50% of the oracle gap →
What ships
■ A reusable distillation recipe for closing oracle gaps in workflow-conditioned tasks.
■ Calibrated workflow posterior useful for many downstream surgical tasks beyond RSD.
■ Ablation map showing which teacher signals and loss formulations matter.
■ Deployable predictor that approaches the privileged-supervision upper bound under strict prefix-only protocol.
BariatricRSD next-paper proposal · Slide 11 / 18
2026-05-21

## Slide 12
Combined value to the field
What the two papers together let the surgical-AI / vision community do.
THE TWO PAPERS AS A PROGRAM
Do video / world FMs help surgical forecasting?
Quantitative answer with verified causal protocol (Paper 2A)
Is generative pixel quality a good proxy for surgical understanding?
No — community must use task-relevant metrics (Paper 2A diagnostic)
How do we measure surgical-FM transfer fairly?
Strict prefix-only + workflow-variability stratification (Paper 2A)
Can a deployable model recover the privileged workflow gain?
Yes, via privileged-information distillation (Paper 2B)
Does workflow conditioning still matter with stronger backbones?
Yes when H(z) is high; no when H(z) is low (both papers)
BariatricRSD next-paper proposal · Slide 12 / 18
2026-05-21

## Slide 13
Timeline
Phase 0 → Phase 4 with explicit submission milestones.
2026 Q3 — 2027 Q2
Jun-26
Jul-26
Aug-26
Sep-26
Oct-26
Nov-26
Dec-26
Jan-27
Feb-27
Mar-27
Apr-27
May-27
Phase 0: feasibility audit
Phase 1: scout matrix
Phase 2: confirmatory (Paper 2A)
Paper 2A write + submit
Phase 3: Paper 2B start
Phase 4: Paper 2B finish
Phase 0 complete
Phase 1 go/no-go
Paper 2A → MICCAI 2027
Paper 2B → NeurIPS 2027
BariatricRSD next-paper proposal · Slide 13 / 18
2026-05-21

## Slide 14
Compute budget & risk gates
Staged plan: <500 GPU-h to first go/no-go decision.
STAGE-BY-STAGE COSTS WITH MITIGATIONS
Stage
GPU-hours
Cost ($)
Cumulative ($)
Decision gate
Stage 0 — feasibility
40–80
$250
$250
Audit backbones; drop brittle ones
Stage 1 — scout matrix
250–500
$0.75K–$1.5K
$1.0K–$1.75K
Any FM improves causal RSD by ≥0.3 min?
Stage 2 — confirmatory
700–1,400
$2.1K–$4.2K
$3.1K–$6.0K
Lock Paper 2A matrix; ≥3 claims defensible?
Stage 3 — adapters
500–1,200
$1.5K–$3.6K
$4.6K–$9.6K
Worth retraining selected backbones?
Stage 4 — optional SSL
700–1,500
$2.1K–$4.5K
$6.7K–$14.1K
Surgical-SSL adapt only if Stages 2/3 win
Paper 2B (reuses 2A)
750–1,500
$2.25K–$4.5K
$9K–$18.6K
Distillation closes ≥50% of oracle gap?
Full-program upper bound: ~5,000–7,000 GPU-h (~$15K–$21K with 25% overhead)
Tier 1 alone (Phase 0 + Phase 1) costs <$2K — enough to decide whether either paper is viable.
BariatricRSD next-paper proposal · Slide 14 / 18
2026-05-21

## Slide 15
Risk hedge — what ships if Cosmos doesn't transfer
Pre-register the diagnostic framing before running Cosmos experiments.
‘COSMOS-IS-MEH’ RECOVERY NARRATIVE
Most likely empirical outcome: Cosmos doesn't beat ViT-B/16 on surgical forecasting (natural-world pretraining ≠ endoscopic close-ups).
NARRATIVE 1 (primary)
Pixel-prediction quality is a weak proxy for surgical forecasting.
Cosmos generates clean pixels but mid-pack features. The diagnostic itself is the contribution.
NARRATIVE 2
Domain gap dominates; surgical-native FMs win.
Cosmos < ViT-B/16 < SurgMotion / SurgVISTA. Quantifies the surgical-domain gap; motivates Paper 2B.
NARRATIVE 3 (fallback)
Cosmos as calibration anchor.
Even if no FM wins, Cosmos in the matrix tells the field when surgical pretraining specifically helps.
Tactic: decide and document the framing **before** running Cosmos experiments. If Cosmos wins → pivot to positive story; if it loses → the pre-committed paper still ships.
BariatricRSD next-paper proposal · Slide 15 / 18
2026-05-21

## Slide 16
What we deliberately avoid
Framing traps that would make the papers harder to defend.
GUARDRAILS
Won't do
■ Vendor-first framing — "NVIDIA Cosmos + OpenUSD for surgery" reads as product adoption.
■ First-surgical-FM claim — the field already has SurgMotion, SurgVISTA, ZEN, EndoMamba.
■ OpenUSD as decoration — if a flat JSON gives the same signal, USD isn't load-bearing.
■ Full Cosmos fine-tuning as the first move — too expensive without prior evidence of transfer.
■ Single-fold headline numbers — the field expects 5-fold + cross-center + paired stats.
■ Claiming clinical readiness — these are benchmark / method papers, not deployment papers.
Will do
■ Causal evaluation as the apparatus — strict prefix-only, leakage-safe, deployment-relevant.
■ Systematic transfer matrix — physical-AI + general-video + surgical-native FMs all measured.
■ Pre-registered narratives — Cosmos-meh diagnostic framing decided before running experiments.
■ Staged compute — <$2K to first go/no-go, full program only if signal exists.
■ 5-fold MB140 + cross-center + paired bootstrap — reviewer-proof stats.
■ Releasable artifacts — code, leaderboard, feature caches, manifests.
BariatricRSD next-paper proposal · Slide 16 / 18
2026-05-21

## Slide 17
Open questions for external review
Top items I want reviewer / collaborator pushback on.
ASK ME ABOUT THESE
■ Is the two-paper split the right call? Or would the field reward one comprehensive paper?
■ Is Cosmos the right physical-AI baseline? Should V-JEPA 2.1 + SurgMotion be the primary FM pair?
■ Venue fit for Paper 2A — MICCAI 2027 or CVPR 2027?
■ Venue fit for Paper 2B — does the privileged-information distillation framing clear NeurIPS / ICLR?
■ Is the diagnostic claim a real contribution or face-saving framing? How would a vision reviewer read it?
■ Is the compute budget realistic ($21K full upper bound) or should we scope to Stage 1 first?
■ Is there a recent surgical-FM paper from mid-2026 that we've missed?
■ OpenUSD side experiment — cut entirely or keep as appendix?
■ Variability-scaling thesis for anticipation tasks — does H(z) still measure the right thing?
■ Cross-procedure generalization — push to 4 procedures (MB140 + Cholec80 + AutoLaparo + CholecT50) or stay focused?
BariatricRSD next-paper proposal · Slide 17 / 18
2026-05-21

## Slide 18
Bottom line
Two papers, sequenced. Paper 2A first (decision-gated), then Paper 2B on shared infrastructure.
■ Flagship contribution: causal-evaluation apparatus + variability-scaling generalization.
■ Cosmos and OpenUSD: in the matrix, not in the title.
■ Budget: <$2K to first go/no-go; ~$15K–$21K for the full two-paper program.
■ Schedule: Paper 2A → MICCAI 2027 (Mar); Paper 2B → NeurIPS 2027 (May).
■ Both papers ship even if Cosmos doesn't transfer — the apparatus and the method are the contributions.
Companion docs: NEXT_PAPER_BRIEF.md · NEXT_PAPER_PLAN.md
BariatricRSD next-paper proposal · Slide 18 / 18
2026-05-21